## Project Planning Template_model
Project Title
Student Consultant Activities | Staff Activities | Project Benchmarks | Project Benchmark Indicators | Date Assigned | Date Due
1. Assign COA Narrative to Nancy as lead | OPEN: to complete questions 1-5 | · Have a document describing detailed responses to questions | Approved document for RPM standard questions |  | 11/12/2009 (Nancy); ;
2. Assign description of the RPM system utilized by the agency to ensure compliance with applicable licenses, regulations and decrees in RPM narrative 3; gather letter signed by chair & CEC certifying the organization is in compliance with license requirements, regulations and decrees. | · Kathy Henderson to complete with assistance from archdiocese/Evelyn/RiskManagement | · Gather information from Archdiocese and Evelyn. | · Completed list with required information. | 2010-01-19 | 2010-02-09
4 Assign procedure for quarterly reivew of incidents, accidents and grievances | Missy (already assigned) | Schedule meeting to discuss info and on-site doc requirements | Finalized procedure and policy | 2010-01-14 | 2010-01-28
5. Complete NA paperwork for RPM 3; Medication Control and Administration | Kathy Henderson; wait until March | Review standard | Completed NA paperwork
6. Assign adherence to RPM 4 relating to insurance policies; need list of insurance policies with descriptions, amounts and dates of coverage | Missy (already assigned) | Get Missy to gather policy information; create document for notificaton to employees | Finalized PE template, procedure, and contract policy and procedures | 2010-01-14 | 2010-02-11
7. Assign Case record access policies and procedures to Jackie | Jackie to work with Yvonne for information. | Jackie to notify Yvonne and Kim of need to create poliy and procedure for staff and volunteers | Finalized policy and procedre | 2010-01-19 | 2010-02-16
8. Assign contract and service agreements procedures; and monitoring procedures | Kathy and Jack on current contracts (vendor and service contracts only) very few at this point. | Jack and Kathy to gather current contracts in place; ask other social service agencies for existing contract procedures and monitoring procedures; some board members may be helpful | Finalized list of contracts/MOU's with procedures for monitoring and writing | 2010-02-09 | 2010-03-02

## Blank Template
Project Title
Project Manager (Consultant) Activities | Staff Activities | Project Benchmarks | Project Benchmark Indicators | Date Assigned | Date Due